## Wx
PROJECT REPORT
Group | <Group 1>
Week | <27/06/2022-01/07/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS Document | In Progress | Edit and add information of part 2 SRS document
2 | Design Document | In Progress | Edit and add information of part 2,3 SRS document
3 | Implement Iteration 3 | In Progress | Coding each feature
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Database designe | All member | Designe database follow the functions of project
2 | Order Information | QuangHD | Add information in SRS, Design document and coding
3 | Settings List | QuangHD | Add information in SRS, Design document and coding
4 | Setting Details | QuangHD | Add information in SRS, Design document and coding
5 | Feedbacks List | HieuLD | Add information in SRS, Design document and coding
6 | Product Details - Public | HieuLD | Add information in SRS, Design document and coding
7 | Cart Details | HieuNV | Add information in SRS, Design document and coding
8 | Cart Contact | HieuNV | Add information in SRS, Design document and coding
9 | Feedback Details | HoanNK | Add information in SRS, Design document and coding
10 | Orders List | HoanNK | Add information in SRS, Design document and coding
11 | Order Details | HoanNK | Add information in SRS, Design document and coding
12 | Cart Completion | TienPM | Add information in SRS, Design document and coding
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Checking and modifile all project | 2022-10-07 | All member in team must checking all project to modifile where is not good
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C26: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue